PMGT 699-91- O-2025

Late Spring

Applied Project Management II

Rizwan Khan

Sai Chaitanya Yadav Motor

Dept of Project Management

Harrisburg University of Science and Technology

Project Management

310519

Contents

1.Executive Summary	3

2. Activities Completed This Period	3

3. Activities Planned for the Next Period (May 16 – May 31, 2025)	5

4. Milestone Schedule	5

5. Project Issues	6

	Resource Availability:	6

	Vendor API Delay Risk:	6

	Tool Access Delay:	6

6. Project Risks	7

7. Financial Summary	8

A. Baseline Cost estimate	8

B. Revised Cost Estimate (Post Change Request)	9

C. Justification for Cost Increase	9

D. Executive Insight	10

8. Change Control Summary	10

Summary	10

Impact:	10

Approval & Implementation:	11

Conclusion and Recommendations	11

References	11

# 1.Executive Summary

The GYS (Get Your Stock) mobile application project has officially commenced with strong momentum. During the first two weeks of implementation, several foundational activities have been successfully completed, including project kickoff, team onboarding, and project environment setup. A change request was submitted and approved by the project sponsor during Week 1, resulting in a revised timeline and an increase in project cost by 10%.

Despite minor resource challenges, the project remains on track to meet strategic objectives and is aligned with the original scope. The current focus is on progressing through core development milestones while proactively addressing potential risks.

# 2. Activities Completed This Period

- Kickoff Meeting Conducted (May 2, 2025): Stakeholders, technical teams, and business sponsors aligned on project objectives, scope, and deliverables.

- Project Charter Finalized & Approved (May 4, 2025): Includes scope, key deliverables, high-level schedule, and team structure.

- Project Environment Setup Completed (May 6, 2025): Development and testing environments configured with access granted to respective team members.

- Initial Requirements Review with Business Analyst (May 8, 2025): Product backlog items groomed and prioritized.

- Change Request Approved (May 10, 2025): Timeline and budget adjusted based on scope expansion.

| Activity | Description | Completion Date |
| --- | --- | --- |
| Kickoff Meeting Conducted | Project officially launched with alignment on goals, scope, and responsibilities | May 2, 2025 |
| Project Charter Finalized & Approved | Charter approved by sponsor, defining scope, stakeholders, and objectives | May 4, 2025 |
| Project Environment Setup Completed | Development and testing environments configured and accessed | May 6, 2025 |
| Initial Requirements Review with Business Analyst | Reviewed and prioritized product backlog items with the BA | May 8, 2025 |
| Change Request Approved | Sponsor approved 10% increase in cost and schedule due to scope expansion | May 10, 2025 |

The table above summarizes the key project activities successfully completed during the first two weeks of the GYS project.

# 3. Activities Planned for the Next Period (May 16 – May 31, 2025)

- Completion of detailed UI/UX wireframes

- Backend database schema development (MongoDB)

- Initial API design for vendor integration

- Development of login and authentication module

- Conduct Sprint 1 Review and Sprint 2 Planning

# 4. Milestone Schedule

The table below outlines the key project milestones for the GYS project, capturing both planned and actual completion dates, current status, responsible owners, and relevant notes to ensure transparency and accountability throughout the project lifecycle.

| Milestone | Planned Completion Date | Actual Completion Date | Status | Owner | Notes |
| --- | --- | --- | --- | --- | --- |
| Project Kickoff | May 2, 2025 | May 2, 2025 | Completed | Project Manager | All stakeholders participated; project scope confirmed. |
| Project Charter Approval | May 4, 2025 | May 4, 2025 | Completed | Project Sponsor | Charter signed off with documented goals and deliverables. |
| Change Request Implementation | May 10, 2025 | May 10, 2025 | Completed | Project Manager | Revised scope approved, impacting cost and timeline by 10%. |
| UI/UX Wireframe Completion | May 20, 2025 | In Progress | In Progress | UI/UX Designer | Wireframe designs for key modules underway. |
| Sprint 1 Development Cycle Begins | May 22, 2025 | Scheduled | Not Started | Development Lead | To begin upon wireframe finalization. |

# 5. Project Issues

- Resource Availability:

One assigned developer will be unavailable throughout June due to unforeseen personal reasons. Another developer may be unavailable next week, which may delay UI/UX delivery.

- Vendor API Delay Risk:

Awaiting documentation from delivery partners, which could impact integration timelines.

- Tool Access Delay:

One team member experienced access issues to testing tools; issue resolved on May 13.

# 6. Project Risks

The table above outlines identified project risks, their potential impacts, responsible owners, and corresponding mitigation and contingency strategies to ensure proactive risk management throughout the GYS project lifecycle.

| Risk ID | Risk Description | Likelihood | Impact Level | Owner | Status | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Resource Unavailability | High | Medium | Project Manager | Active | Reassign tasks to available team members; start contract resource onboarding process |
| R-002 | Delay in Vendor API Documentation | Medium | High | Backend Developer Lead | Active | Use mock APIs to proceed with development; escalate issue in weekly vendor call |
| R-003 | Scope Creep from Stakeholder Requests | Medium | High | Business Analyst | Under Monitoring | Strict enforcement of change control process; require written sponsor approval |
| R-004 | Dependency on Third-party Payment Gateway | Low | Medium | Technical Architect | Identified | Early integration testing; confirm sandbox credentials and support contacts |
| R-005 | Development Tool Access Issues | Medium | Low | DevOps Engineer | Mitigated | Pre-create user accounts; conduct onboarding checklist for every new team member |

# 7. Financial Summary

The financial health of the GYS (Get Your Stock) project is critical to ensuring that the proposed features and delivery timelines are met without compromising quality. The original budget was developed during the project planning phase based on anticipated scope, resource availability, and a fixed development window. However, a change request approved during Week 1 resulted in a necessary revision of both cost and schedule. The financial summary below presents a comparative analysis of baseline vs. revised financials, highlights the reasons for adjustments, and discusses the implications for project stakeholders.

## A. Baseline Cost estimate

| Category | Estimated Cost (USD) |
| --- | --- |
| Project Management | $5,000 |
| Business Analysis | $4,000 |
| UI/UX Design | $3,500 |
| Frontend & Backend Dev | $10,000 |
| Quality Assurance (QA) | $4,000 |
| DevOps & Hosting | $2,500 |
| Miscellaneous/Contingency | $1,500 |
| Total Baseline Cost | $30,500 |

The baseline was established with efficient resource allocation and lean operations in mind. Initial development was to be completed using internal resources and standard cloud infrastructure with minimal third-party integrations.

## B. Revised Cost Estimate (Post Change Request)

| Category | Updated Cost (USD) |
| --- | --- |
| Project Management | $5,500 |
| Business Analysis | $4,200 |
| UI/UX Design | $4,000 |
| Frontend & Backend Dev | $11,000 |
| Quality Assurance (QA) | $4,400 |
| DevOps & Hosting | $2,800 |
| Miscellaneous/Contingency | $2,000 |
| Total Revised Cost | $33,900 |

The increase of approximately $3,400 reflects an overall 11.1% increase in project cost. This change was driven by the approved change request in Week 1, which added new features to improve inventory tracking and user dashboard personalization—both of which required additional design, development, and testing time.

## C. Justification for Cost Increase

- Scope Expansion: The change request included the addition of real-time stock synchronization with vendors and predictive analytics for restaurant owners, which added development and QA workload.

- Resource Adjustments: One developer had to be substituted with an external contractor for sprint 2 due to unavailability, increasing hourly billing.

- Contingency Usage: A portion of the contingency was utilized to mitigate risks associated with third-party API integration delays.

## D. Executive Insight

While the increase in project cost may raise initial concerns, the additional investment is aligned with enhancing the product’s value proposition. The inclusion of predictive inventory analytics and enhanced user dashboards will support broader market adoption and competitive differentiation. The revised financials remain justifiable and controlled, with a strong emphasis on ROI-focused execution moving forward.

# 8. Change Control Summary

Change Request ID: CR-001-GYS
Title: Functional Scope Enhancement – Vendor Integration & Analytics
Submitted On: May 7, 2025
Status: Approved

Summary:
A change request was raised to expand the GYS application’s scope by adding:

- Auto-scheduling for delivery vendors via third-party API integration.

- Inventory analytics dashboard with real-time tracking and visual reporting.

These features align with strategic goals to improve automation and decision-making capabilities for users.

## Impact:

- Schedule: Extended by 10% to accommodate additional development and testing.

- Cost: Increased from $50,000 to $55,000 due to added design, backend, and QA efforts.

- Resources: Minor adjustments in assignments and timelines to absorb added work.

## Approval & Implementation:

- Approved by the Project Sponsor on May 10, 2025.

- Updates integrated into the revised project schedule and communicated to all stakeholders.

# Conclusion and Recommendations

The GYS project is progressing steadily with key early-phase deliverables completed. The project team is fully engaged, and stakeholder communication is ongoing. Immediate attention is being given to mitigating resource availability risks and maintaining velocity during development sprints. Stakeholders are advised to review the upcoming risk mitigation proposals and support contractor onboarding, if required.

# References

- Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK® guide) (7th ed.). Project Management Institute.

- Schwalbe, K. (2021). Information technology project management (9th ed.). Cengage Learning.

- Kerzner, H. (2022). Project management: A systems approach to planning, scheduling, and controlling (13th ed.). Wiley.

- Heldman, K. (2021). PMP: Project Management Professional Exam Study Guide (10th ed.). Wiley.